## Task Summary
| Name | Petchimuthu Maharajan (2597)
| Role | Trainee Consultant - Oracle Technical
| Github Link | https://github.com/PETCHIMUTHU-M/fusion
| Mentor 1 | Arun Gopalarathnam
| Mentor 2 | Mohamedasifkhana Ahamedkabir
| Mentor 3 | Saravanan Kumarappa
| Mentor 4 | Benin Tharmalingam
Task No | Task Date | Task Title | Completed Date | Documented
Task 1 | 2021-06-16 | Bi Report - RTF Template with multiple layout | 2021-06-22 | Y
Task 2 | 2021-06-17 | OTBI Report - Master-Details & Action Links | 2021-06-18 | Y
Task 3 | 2021-06-23 | Bi Report - EXCEL Template | 2021-06-23 | Y
Task 4 | 2021-06-23 | Bi Report - RTF Template with EXCEL output | 2021-06-23 | Y
Task 5 | 2021-06-24 | Bi Report - Bursting | 2021-06-24 | Y
Task 6 | 2021-06-25 | Bi Report - Parameters and Multiple Sheet | 2021-06-28 | Y
Task 7 | 2021-06-25 | Security Console | 2021-06-28 | Y
Task 8 | 2021-06-28 | SQL - Sequence Generate | 2021-06-29 | Y
Task 9 | 2021-06-28 | Bi - Dynamic logo and page number based on customer | 2021-06-30 | Y
Task 10 | 2021-06-28 | Bi - Record limit in RTF | 2021-06-30 | Y
Task 11 | 2021-07-02 | Bi - Purchase Order Detailed Report | 2021-07-09 | Y
Task 12 | 2021-07-06 | SQL - Joins, Set Operators and Functions | 2021-07-06 | Y
Task 13 | 2021-07-06 | SQL - Fusion table queries | 2021-07-28 | Y
Task 14 | 2021-07-09 | OTBI - View Selector | 2021-07-09 | Y
Task 15 | 2021-07-12 | Bi - Report Properties | 2021-07-16 | Y
Task 16 | 2021-07-15 | Bi - SCM Reports | 2021-07-15 | Y
Task 17 | 2021-07-16 | Bi - AP Aging report | 2021-07-27 | Y
Task 18 | 2021-07-19 | Bi - Ar Aging report | 2021-07-28 | Y
Task 19 | 2021-07-20 | Bi - Sales Order Detailed Report | 2021-08-02 | Y
Task 20 | 2021-08-16 | E-text - Citi Bank | 2021-08-20
Task 21 | 2021-08-20 | E-text - HDFC Bank | 2021-08-25
Task 22 | 2021-08-24 | E-text - MNG | 2021-08-25
Task 23 | 2021-08-25 | E-text - Citi Bank CHQ | 2021-08-30
Task 24 | 2021-09-01 | XSLT - BNPP Bank | 2021-09-06
Task 25 | 2021-09-07 | XSLT - UOB Bank | 2021-09-08
Task 26 | 2021-09-09 | E-text - Kotak Mahindra Bank | 2021-09-09
Task 27 | 2021-09-13 | E-text - CIMB Bank

## Daily Tracker
Date | Task No | Forenoon | Afternoon | Status - Comments
2021-06-16 | Task1 | Creation of data set and data model | Layout generation | Sample report created
2021-06-17 | Task 2 | Master-Details Events | Action Links | Sample report created
2021-06-18 | Task 1,2 | OTBI report generated | Working BI Multiple Layout | Task 2 completed
2021-06-21 | Task 1 | Working on multiple layouts | Task1 documentation | Task 1 completed
2021-06-22 | Task 1 | Data Model Alteration | Working BI Multiple Layout | Task 1 updated
2021-06-23 | Task 3,4 | Excel Templates | Excel output | Task 3&4 completed
2021-06-24 | Task 3,4,5 | Documentation | Bursting Concepts | Task 5 completed
2021-06-25 | Nil | Bursting and Column Links | ESS jobs | Bi topics Revised
2021-06-28 | Task 6,7 | Security Console | Multiple Sheets | Task 6,7 competed
2021-06-29 | Task 8,9 | Seqence Generate | Dynamic logo | Task 8 completed
2021-06-30 | Task 9,10 | Dynamic Logo and page number | Limiting Records in pages | Task 9,10 completed
2021-07-01 | Nil | Fusion Tables Documentation | OTBI - Analysis revising | Revised and documented
2021-07-02 | Task 11 | FSD analysis | Table and Column identification | Task 11 analysed
2021-07-05 | Task 11 | Creation of data model | Generating EXCEL template | Task 11 template generated
2021-07-06 | Task 12 | Properties - Data Model and Report | SQL Documentation | Task 12 completed
2021-07-07 | Task 13 | SQL Function Presentation | Supplier, PO, AP table queries | Presentation Completed
2021-07-08 | Task 13 | SQL Function Presentation | Customer, OM, AR | Presentation Completed
2021-07-09 | Task 11,13,14 | SQL queries and PO report | View Selector in OTBI | Task 11,14 completed
2021-07-12 | Task 13,15 | Documentation and SQL queries | Report properties | Documents updated
2021-07-13 | Task 15 | Report properties | Documentation - Report properties | Task 15 documented
2021-07-14 | Task 15 | Report properties - Formatting | Report properties - Format mask | Document updated
2021-07-15 | Task 16 | SCM Reports - AP Invoice report | SCM Reports - AP Invoice report | Task 16 completed
2021-07-16 | Task 17 | Analysed Ap Aging Report | Worked On Ap Aging Report | Task 17 analysed
2021-07-19 | Task 18 | Analysed Ar Aging Report | Worked On Ar Aging Report | Task 17 completed
2021-07-20 | Task 19 | Analysed Sales Order Report | Worked On Sales Order Report | Task 18 completed
2021-07-21 | Task 19 | Worked On Sales Order Report | Review on Ap aging report | Task 17 completed
2021-07-22 | Nil | Ap aging model query analysed | Ap aging model query analysed | Model query analysed
2021-07-23 | Nil | Ap aging model query analysed | Ap aging model query analysed | Model query analysed
2021-07-26 | Task 17 | Data model updation | Data model updation | Task 17 updated
2021-07-27 | Task 17 | Layout generation | Report generation | Task 17 completed
2021-07-28 | Task 18 | Analysed Ar Aging Report | Worked On Ar Aging Report | Task 18 updated
2021-07-29 | Task 19 | Analysed Sales Order Report | Analysed Sales Order Report | Task 19 analysed
2021-07-30 | Task 19 | Worked On Sales Order Report | Worked On Sales Order Report | Task 19 DM created
2021-08-02 | Task 19 | Sales Order Report Generated | Documentation for reports | Task 19 updated
2021-08-03 | Nil | Re-analysing Ap aging query | Re-analysing Ap aging query | Query analysed and documented
2021-08-04 | Nil | Analyzing various tables in Ap aging query | Analyzing various tables in Ap aging query | Query analysed and documented
2021-08-05 | Nil | Analyzing sub-queries in AP aging main query | Analyzing sub-queries in AP aging main query | Query analysed and documented
2021-08-06 | Nil | Analyzing conditions and joins in AP aging query | Analyzing conditions and joins in AP aging query | Query analysed and documented
2021-08-09 | Nil | Review on Ap Aging report | Re-analysing Ap aging query | Ap Aging analysed
2021-08-10 | Task 17 | Type of Invoices | Accounting of Invoices | Ap Aging analysed
2021-08-11 | Task 17 | Accounts Payables | Accounts Payables | Analysing AP
2021-08-12 | Nil | Preparation for Review on Ap aging | Ap aging Review | Final Review completed
2021-08-13 | Nil | Analysing about XML and XPATH | Analysing e-text template format | Analysed
2021-08-16 | Nil | Creating sample E-text report | Discussion on Bank interface | Report created & Files shared
2021-08-17 | Task 20 | E-text - FSD Analysis | E-text - Mapping doc Analysis | Task 20 analysed
2021-08-18 | Task 20 | Etext template creation | Template review | Task 20 template created
2021-08-19 | Task 20 | Template alteration | Sample output using BI Template Viewer | Citi Bank assignment completed
2021-08-20 | Task 21 | Template creation | CitiBank Template alteration | Citi Bank assignment updated
2021-08-23 | Task 21 | Template Creation | Etext - Processes, flow and review | Review completed Etext overview
2021-08-24 | Task 21 | HDFC template | HDFC updation | Task 21 completed
2021-08-25 | Task 21, 22 | MNG updation | HDFC updation | Task 22 completed
2021-08-26 | Task 23 | Citi CHQ Mapping analysis | Citi CHQ Template creation | Template generated
2021-08-27 | Task 23 | Citi CHQ Template creation | Citi CHQ Template creation | Template altered
2021-08-30 | Task 23 | Working on altered payment file | Template created for new mapping sheet | Task 23 completed
2021-08-31 | Nil | Preparation for Review on E-text | Documentation and review | Review completed on E-text
2021-09-01 | Nil | Training on Citi Bank assignment | Analysing BNPP Bank Files | Analysed BNPP Bank
2021-09-02 | Task 24 | BNPP XSLT template creation | BNPP XSLT template creation | BNPP XSLT template created partially
2021-09-03 | Task 24 | BNPP XSLT template alteration | BNPP XSLT output created | Task 24 completed
2021-09-06 | Task 24 | BNPP XSLT template alteration | BNPP XSLT output created | Task 24 updated
2021-09-07 | Task 25 | XSLT Revised | UOB analysed | Task 25 analysed
2021-09-08 | Task 25 | UOB Template created | UOB output generated and Mock review | Task 25 and Mock review completed
2021-09-09 | Task 26 | Kotak EText template | Bank Payment Review and output verified. | Task 26 completed
2021-09-13 | Task 27 | FSD Analysis | Mapping Sheet creation. | Mapping Sheet created.
2021-09-14 | Task 28 | Template creation. | Output generation. | Output generated