## Task Summary
Fusion | BI and OTBI
Mentors | Arun Gopalarathnam
Mohamedasifkhana Ahamedkabir
Name | Petchimuthu Maharajan (2597)
Task No | Task Title | Task Description | Task Type | Planned Start Date | Planned End Date | Resource Name | Planned Hours
1 | Bi Report - RTF Template with multiple layout | Bi Report - RTF Template with multiple layout | Technical Support | 2021-06-28 | 2021-06-29 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
2 | OTBI Report - Master-Details & Action Links | OTBI Report - Master-Details & Action Links | Technical Support | 2021-06-30 | 2021-06-30 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
3 | Bi Report - EXCEL Template | Bi Report - EXCEL Template | Technical Support | 2021-07-01 | 2021-07-01 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
4 | Bi Report - RTF Template with EXCEL output | Bi Report - RTF Template with EXCEL output | Technical Support | 2021-07-02 | 2021-07-02 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
5 | Bi Report - Bursting | Bi Report - Bursting | Technical Support | 2021-07-05 | 2021-07-05 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
6 | Bi Report - Parameters and Multiple Sheet | Bi Report - Parameters and Multiple Sheet | Technical Support | 2021-07-06 | 2021-07-07 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
7 | Security Console | Security Console | Technical Support | 2021-07-08 | 2021-07-08 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
8 | SQL - Order management | SQL - Order management | Technical Support | 2021-07-09 | 2021-07-09 | mohamedasifkhana.ahamedkabir@chainsys.com | 8
9 | Bi - Dynamic logo and page number based on customer | Bi - Dynamic logo and page number based on customer | Technical Support | 2021-07-12 | 2021-07-13 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
10 | Bi - Record limit in RTF Template | Bi - Record limit in RTF Template | Technical Support | 2021-07-14 | 2021-07-15 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
11 | Sales Order Details | Sales Order Details | Technical Support | 2021-07-16 | 2021-07-19 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
12 | Purchase Order Details | Purchase Order Details | Technical Support | 2021-07-20 | 2021-07-21 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
13 | AR Aging Report | AR Aging Report | Technical Support | 2021-07-22 | 2021-07-23 | mohamedasifkhana.ahamedkabir@chainsys.com | 16
14 | AP Aging Report | AP Aging Report | Technical Support | 2021-07-26 | 2021-07-27 | mohamedasifkhana.ahamedkabir@chainsys.com | 16